## DRN,DRL
DOCUMENT RELEASE NOTICE
This Unified Project Plan Template document, Version 6.01, is released for use in Tata Consultancy Services Limited (TCS) with effect from 01/June/2009. / This document is subject to TCS Document Control Procedure. / Softcopy of the latest version of the d

Revision Details:
Version No./Revision No.	Release Date	Change type (add/ del/chg)	Worksheet Name and section	Revision description
6.01	1-Jun-09	Add	Quality & Reuse Plan	Inclusion of reference to MDPs in the metrics section
6.01	1-Jun-09	Add	Staffing & Training plan	Inclusion of reference to existing staffing plan maintained by the project
6.00	1-Sep-08	Chg	All	Modified the template to reflect the / reorganization, standardized to include branch tailoring, to improve the / user friendliness of the template.

## Read Me
Tata Consultancy Services Limited Unified Project Plan Template: 6.01

June 2009
Overview of Unified Project Plan (UPP)
The UPP is the project planning reference document and is intended to assist the project teams in the execution of their project as well as meeting the defined quality objectives. This document needs to be updated during the entire life cycle of the proje

Note: / 1. This note is meant for guidance. / 2. Instructions are provided in black colour italics text, across the various sections and worksheets / 3. Text that needs to be retained as part of the plan is given in black colour normal font.

## Cover Page
Unified Project Plan
For
F&O IIP Integration_Q2 T&M					<Project Name>

Version 0.1

IS-Telecom1-Parent / IS-Telecom1.1-Group1

January, 2009

Revision Details:
Version No./ Revision No.		Release Date	Change type (add/ del/chg)		Worksheet Name/ Section			Revision description
1.0		1/11/2004	Add					First version of the project plan
2.0		1/4/2006	Chg					UPP template change for IQMS ver 2.0 changes
3.0		19/05/2006	Add					TL9000 updates
3.1		24/11/2006	Chg					WON change
3.2		20/04/2007	Add					PAL details included
3.3		18/09/2007	Chg					Change in team size / Added new risks
3.4		25/11/2008	Chg					WON Change
3.5		29/01/2009	Add		All sheets			UPP template change for IQMS
3.6		20/05/2009	Chg		Project Synopsis, Governance plan, Risk Mgmt Plan, Configuration Mgmt			Updated UPP for Q1 2009
3.7		9/11/2009	Add		DRN,DRL , ReadMe , Quality&Reuse Plan, Staffing & Training Plan sheet where updated as per Template 6.01			UPP updated with the UPP template 6.01 version

This document and any revisions are subject to document control. Please keep them up-to-date using the release notice from the distributor of the document.

Approved By:		K Jaiganesh					Date:

Authorized By		Ag Bharathan					Date:

## TOC
Table of Content

S.No	Worksheet Name	Contents
1	List of Abbreviations	Abbreviations
2	Project Synopsis	1. Project Objectives and Scope
		2. Project Overview
		3. Statutory and Regulatory requirements
		4. Assumptions, Dependencies and Constraints
		5. Project Deliverables
		6. Project Standards & Reference
		7. Master Schedule and Detailed Plan
3	Governance Plan	1. Organization Structure
		2. TCS teams - Roles & Responsibilities
		3. Client Communication Plan
		4. Project Monitoring and Control Plan
4	Stakeholder Matrix	1. Stakeholder Interaction Matrix
5	Risk Management plan	1. Risks - Project
		2. Risks - Information Asset
6	Quality and Reuse Plan	1. Quality Plan
		Metrics
		Review Plan
		Test Plan
		2. Defect Prevention Plan
		3. Problem Reporting and Corrective Action
		4. Process Improvement Initiatives
		5. Records Collection, Maintenance and Retention
		6. Reuse Plan
7	Configuration Management plan	1. Responsibilities
		2. Configuration Identification
		3. Change Management
		4. Software Library Structure
		5. Code and Media Control
		6. Business Continuity Plan
		7. Traceability Strategy
8	IT Infrastructure Plan	1. Hardware, Software and Programming language requirements
		2.Tools Used
9	Staffing and Training plan	1. Staffing Plan
		2. Training Plan
10	OPD	1. Operational Process Definition
11	IOU specific procedures	1. Telecom projects
		2. Aerospace projects
		3. Medical devices projects
		4. Infrastructure Services projects

## Abbreviations
List of Abbreviations	TOC

Abbreviation	Expanded form
ACM	Audit and Compliance Manager
ACT	Audit and Compliance Team
APT	Audit Processing Tool
ASG	Application Support Group
BCP	Business Continuity Plan
BRM	Business Relationship Manager
BAG	Branch Audit Group
BT Plc	British Telecommunications Plc
CI	Configurable Item
CML	Crisis Management Lead
CMP	Crisis Management Plan
CR	Change Request
CSI	Customer Satisfaction Index
CSP	Client Supplied Product
CSS	Customer Satisfaction Survey
CP	Communication Providers
CIT	Component Integration Testing
DAG	Delivery Assurance Group
DAR	Decision Analysis and Resolution
DP	Defect Prevention
DR	Disaster Recovery
DCH	Delivery Centre Head
EQA	External Quality Assurance
FI	Final Inspection
FMEA	Failure Mode Effect Analysis
FP	Fixed Price
FOA	First Order Applications
GL	Group Leader
HLD	High Level Design
HR	Human Resource
iEST	Integrated Software Estimation Tool
IOU	Independent Operating Unit
IPMS	Integrated Project Management System
IQA	Internal Quality Assurance
iQMS	Integrated Quality Management System
ISM	Information Security Manager
IVV&T	Integrated data Validation Verification & Testing
LLD	Low Level Design
MCA	Mission Critical Application
ML	Module Leader
MSA	Master Service Agreement
MCC	Migration Control Centre
MSAN	Multi Service Access Node
OPD	Operational Process Definition
PCB	Process Capability Baselines
PE	Process Excellence
PL	Project Leader
PMR	Project Management Review
QAM	Quality Assurance Manager
QR	Quality Reviewer
RMG	Resource Management Group
SCM	Software Configuration Management
SDO	Service Delivery Organisation
SMP	Software Metrics Program
SOW	Statement of Work
SDLC	Software Development Life Cycle
SIP	Service Improvement Plan
STT	Switch Threshold Tool
T&M	Time and Material
TDCE	Total Defect Containment Effectiveness
TM	Team Member
TO	Task Order
TEMT	Transfer Engineering Migration Tool
TE	Transfer Engineering
UAT	User Acceptance Test
UMP	Unified Metrics Program
UPP	Unified Project Plan
UTS	Unit Test Specification
UTR	Unit Test Results
UTP	Unit Test Plan
UII	Unified Inventory Interface
WON	Work Order Number
WR	Work Request
20CN	20th Century Network
21CN	21st Century Network

## Project Synopsis
Project Synopsis					TOC

Project Name		F&O_IIP_SFW_Offshore_Q2
Customer Name		British Telecommunications Plc
Project ID		800037383
Project WON		2129408
IOU		IS-Telecom1-Parent
Sub IOU		IS-Telecom1.1-Group1
Project Location (Offshore; Onsite)		Offshore: Chennai -1, IT Park, Pallavaram – Thoraipakkam, Chennai - 6000096 / Onsite: BT, Ipswich,Bellfast,London,Glasgow United Kingdom

1. Project Objectives and Scope
Project Objectives:		IMB: Design, Construction, System testing for all enhancements for Integrated Message Broker(IMB). As a Integration messenger IMB recieves request from the calling system and transforms it to the end system's format and forwards it to that end system. Later it recieves a response from the end system, transforms it to the calling system's format and forwards it to the calling system. Here IMB performs mainly as a Transformation engine
		ORHUB: As a Integration messenger HUB recieves request from the calling system and transforms it to the end system's format and forwards it to that end system. Later it recieves a response from the end system, transforms it to the calling system's format and forwards it to the calling system. Here Hub performs mainly as a Transformation engine. / Hub's role as a System Aggregator involves recieving the request from the calling system, contacting various end systems, collecting the responses, preparing the output and forwarding it to the calling system. In this case Hub performs a Capability service. / Currently R1000 support is in progress.
		PAL: Design, Construction, System testing for all enhancements for Platform Access Layer (PAL) which interfaces between various sources like BT.com, OneView, Open Reach etc.. PAL supports different programmes like WLR3, RTRCC, SwordFish etc.
Scope exclusions:		Not Applicable

2. Project Overview
Project Type		Development
Nature of Project
Project Size		Medium
Security categorization		Non MCA
Estimation		Peak team strength at offshore is expected to be 121
		Functional Point Estimation is followed in the Project as per the IFPUG Manual available in Ultimatix
		Individual component FP Approach is available in the BT Live link / http://livelink.intra.bt.com/livelink/livelink.exe?func=ll&objId=92491608&objAction=browse&sort=name&viewType=1
Project Start date		5-Jan-04
Expected Project Completion date		As per the latest contract
Project Team size (No.)		Offshore - 121		Onsite - 12
Project Methodology		Agile Methodology is followed for development.
Interface Systems		Being an Integration layer, based on BT Matrix architecture data colation and routing is performed

Hardware		Sun solaris
Software		J2EE, Oracle 9i, UNIX, BEA Weblogic server 8.1 SP4,MQSeries,Weblogic Platform 8.1, IBM MQ V6.0, Tomcat 4.1.31, IBM MB V6.0.0.7
3. Statutory and Regulatory Requirements
None
4. Assumptions, Dependencies and Constraints
Assumptions		a) BT will grant the necessary access to TCS, to all the inputs (Existing System Code, Test data, Test Harness/Stubs, environment, documentation and clarifications) required to carry out its service.
		b)BT will provide the required access for TCS consultants on-site and offshore to work on BT systems
		c)BT will provide the necessary infrastructure for TCS consultants working onsite. This includes the Desks, PCs, phone lines with facility to communicate with TCS offshore.
		d)TCS may not be in a position to meet agreed SLA’s in following exceptional conditions: / • Any failure in relevant hardware components / • Lack of support from BT management/ IT team / • Any delay due to dependency on third parties
		f) BT to have back-to-back SLA’s with various hardware and software vendors which will liaise with TCS
		g) The upgrade of software licenses and software shall be the responsibility of BT. TCS shall provide the information required for the required changes in environment to BT
		i)TCS will review the requirement documents for any CR’s/PR’s or any new enhancements requirements, before start of development to ensure that they have a clear understanding of the requirements. Once TCS is comfortable with the requirements, TCS will proceed with design and development activities.
		j) TCS will not be responsible for purchase of any off-the-shelf products/components or new software if there is a need to purchase one.
		k) Any changes to the requirements scoped for a release would have to go through a change management procedure and revised estimates would be reviewed and agreed between BT and TCS Onsite Project Manager. Changes will be managed through the project CR procedure
		l)BT would provide/make available Subject Matter Experts for query/issue resolution and code/document reviews. BT will provide the review comments and answers to queries within 5 business days
		m)BT would make available Videoconferencing facilities for design presentations/meetings between BT-Exact and TCS, if required
		n) TCS does not expect to have any local servers and its associated software installed in its premises other than what is required for connecting to the BT servers. All activities will be carried out only on the BT servers located at BT premises
		o) BT will provide any software licenses (including licenses for Offshore) if required
		p) Availability of the communication link for software delivery
		q) Any change to the scope of work would be discussed as per the Change Management procedures defined for this engagement
		r) The pricing includes the cost of hardware / software that will be used by the TCS offshore team.
Dependencies		a) Receive signed-off Statement of Requirements and End-to-end Solution Design documents
		b) Design and development schedule of the interfacing component systems – BTWholesale.com, CSS Webservices
		c) Overall Release Management – Setting-up of Release objectives and Strategy, Filtering and Prioritizing Change, Deployment Strategy
		d) Answering and clarifying Requirement/Design Queries & Issues including any queries on the requirements/Solutions for PRs
		e) Development and Testing Environment set-up and Management activities
		f) Reviews of Deliverables – Review of Deliverables including low level design, Code, Unit Test Plan & Results within the accepted timelines
		g) Co-ordination with External Parties – Co-ordination with other parties including OFCOM, BT Wholesale
		h) Conflict Management – Manage any conflict of interests between Release team and any other component, or any other external interfaces
		i) Issue Resolution and Escalation – Guidance in resolving and escalating issues with appropriate parties for speedy resolution
		j) Acceptance Criteria for Confidence Testing to be made available to TCS
		h) Planned Date of acceptance of software by BT wholesale
Constraints		a) Skill set of resources
5. Project Deliverables
Deliverable	Phase	Type (Program, Doc)	Media (Hard copy/ / Soft copy)	Due Date	Recipient	Acceptance Criteria as per contract
Code/Software	Steady State Maintenance	Program	Electronic	As per detailed plan	CIT/E2E Testing	Should fulfill all the requirements mentioned in User Stories
*Unit Test Plan (Optional)	Steady State Maintenance	Document	Electronic	As per detailed plan	CIT/E2E Testing	Code should be successfully deployed & executed
*Unit Test Result / (Optional)	Steady State Maintenance	Document	Electronic	As per detailed plan	CIT/E2E Testing	Test cases shouls be executed n accepted
6. Project Standards & Reference
All project standards and references are available in project repository.
Customer Defined Standards
S.No	Title					Version
1	Agile Practices - Agile Planning, Agile Stand-ups, Retrospectives					*
Project defined standards
S.No	Title					Version
1	TE_Code_Review_Check_List					1.4
Reference Materials
S.No	Title				Publisher/Author	Version
1	Quality Manual				TCS	*
2	Project Procedures Manual				TCS	TCS-iQMS-052
3	Project Planning Guidelines				TCS	TCS-iQMS-102
4	Software Metrics Program				TCS	*
5	Software Estimation Guidelines				TCS	*
6	People process Handbook				TCS	*
7	IPMS Usage Guidelines				TCS	TCS-iQMS-113
8	Business Continuity Planning Process Handbook				TCS	*
9	HR Process Handbook				TCS	*
10	Design Guidelines				TCS	*
11	Testing Guidelines				TCS	*
12	Decision Analysis and Resolution Guidelines				TCS	*
7. Master schedule and Detailed plan
Detailed project plan for every month is available in the project repository \\157.227.128.6\21cn\21CN TE - TEMT\01.Quality Assurance\12.Project Quality Docs\Project Plan

## Responsibility Matrix
Responsibility Matrix					TOC

This will list the responsbility of each person in the project execution

RASCI Definition: / R = Responsible. Role owns the responsibility / A = to whom "R" is accountable. He or She must sign or approve the work before it is OK / S = can be Supportive. Can provide resources or can play a supporting role in implementation / C = should be Consulted. Has information and/or capability necessary to complete the work / I = should be informed. Must be notified of results, but need not be consulted

Steps for using RASCI: / 1. Identify all the processes and activities involved and list them on the left hand side of the table. / 2. Identify all the roles and list them on the top of the chart below the Roles cell / 3. Complete the cells of the chart; Identify who has R, A, S, C, I for each of the activity. / 4. Every process and activity should have only one "R" as a general principle. A gap occurs when an activity does not have an "R". A overlap occurs when multiple roles exist that have an "R" for a given process. / 5. Resolve overlaps. Every process or activity in a role responsibility map should contain only one "R" to indicate a unique process owner. In the case of multiple "R"s, there is a need to further detail the sub processes, to separate the individual responsibilities / 6. Resolve Gaps. When no role has been identified that has an "R" for a process/activity, the individual with authority for role definition must determine which existing or new role is responsible. Update the RASCI map and clarify the role with the individual that assumes the role. / Note: Not all activities will have all components of RASCI.

Responsibility Matrix
Activity	Deliverables	Completion Date					Roles (as applicable to the project)
				Team Member

			Mentor	Team	1	2	3	4	5	6
			Neelam	GR-4	Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
FUNCTIONALITIES
System Requirement Specifications	Scope and Assumptions	15/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
	Use Case	16/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
	Use Case Diagram	17/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
	Domain Model Diagram	18/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
	Test Cases	21/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur
	Class Diagram	21/02/11			Amit Daga	Anuj Khandelwal	Chinmaya Dave	Harshit Khanna	Mohammad Aamir Khan	Vibhor Mathur

Add Patient Details	Scope and Assumptions	15/02/11	Neelam	GR4			Chinmaya Dave
	Use Case	16/02/11					Chinmaya Dave
	Use Case Diagram	17/02/11					Chinmaya Dave
	Domain Model Diagram	18/02/11					Chinmaya Dave
	Test Cases	21/02/11					Chinmaya Dave
	Sequence diagram	21/02/11					Chinmaya Dave
	Code	25/02/11					Chinmaya Dave

Processes Prescription	Scope and Assumptions	15/02/11	Neelam	GR4		Anuj Khandelwal
	Use Case	16/02/11				Anuj Khandelwal
	Use Case Diagram	17/02/11				Anuj Khandelwal
	Domain Model Diagram	18/02/11				Anuj Khandelwal
	Test Cases	21/02/11				Anuj Khandelwal
	Sequence diagram	21/02/11				Anuj Khandelwal
	Code	25/02/11				Anuj Khandelwal

Generate Daily Drug Report	Scope and Assumptions	15/02/11	Neelam	GR4					Mohammad Aamir Khan
	Use Case	16/02/11					Mohammad Aamir Khan
	Use Case Diagram	17/02/11					Mohammad Aamir Khan
	Domain Model Diagram	18/02/11					Mohammad Aamir Khan
	Test Cases	21/02/11					Mohammad Aamir Khan
	Sequence diagram	21/02/11					Mohammad Aamir Khan
	Code	25/02/11					Mohammad Aamir Khan

Generate Drug Status Report	Scope and Assumptions	15/02/11	Neelam	GR4	Amit Daga
	Use Case	16/02/11			Amit Daga
	Use Case Diagram	17/02/11			Amit Daga
	Domain Model Diagram	18/02/11			Amit Daga
	Test Cases	21/02/11			Amit Daga
	Sequence diagram	21/02/11			Amit Daga
	Code	25/02/11			Amit Daga

Order Supply	Scope and Assumptions	15/02/11	Neelam	GR4				Harshit Khanna
	Use Case	16/02/11					Harshit Khanna
	Use Case Diagram	17/02/11					Harshit Khanna
	Domain Model Diagram	18/02/11					Harshit Khanna
	Test Cases	21/02/11					Harshit Khanna
	Sequence diagram	21/02/11					Harshit Khanna
	Code	25/02/11					Harshit Khanna

Update Inventory	Scope and Assumptions	15/02/11	Neelam	GR4					Vibhor Mathur
	Use Case	16/02/11					Vibhor Mathur
	Use Case Diagram	17/02/11					Vibhor Mathur
	Domain Model Diagram	18/02/11					Vibhor Mathur
	Test Cases	21/02/11					Vibhor Mathur
	Sequence diagram	21/02/11					Vibhor Mathur
	Code	25/02/11					Vibhor Mathur

## Stakeholder Matrix
Stakeholder Interaction Matrix					TOC

This will show the administrative and managerial boundaries and interfaces between the project and other stakeholders. This may include subcontractors or vendors and regulatory authorities and client specific boundaries and interfaces, if any.

RASCI Definition: / R = Responsible. Role owns the responsibility / A = to whom "R" is accountable. He or She must sign or approve the work before it is OK / S = can be Supportive. Can provide resources or can play a supporting role in implementation / C = sho

Steps for using RASCI: / 1. Identify all the processes and activities involved and list them on the left hand side of the table. / 2. Identify all the roles and list them on the top of the chart below the Roles cell / 3. Complete the cells of the chart; Iden

Stakeholder Interaction Matrix
Process Area	Activity					Roles (as applicable to the project)
		Client	Supplier/ 3rd party	Onsite	TEG	IOU Head	Sub OU Head	Domain Lead	GL	PL	ML/TL	TM	IVVT	ACM	QAM	PO	Process Primes	RMG	HR	Learning group	SDO	Tech Comm.	ISM/CML	In-house vendor
Customer management	User Stories Signoff	R					I	I	I	I					S
	Testing sign-off	R					I	S	I	R					S
Requirements Development and Management		A					R	S				C
Design and Development		A		R					S	R	R
Verification and Validation		A		S					I		S	S	R
Planning & Monitoring				R					A	R					I
Quantitative Performance Management				R					A	R	R	R			R		R
Configuration Management and Control		S		I					S	R				R			S
Service Management				R		S	S	S	S	R
Product/Service Acquisition and Supplier Management	Identify vendor management team	R				A	R		C	I
	Contract or agreement sign-off	R			S	A	R		I	S
	Ensure that licensing requirements for the tool or reusable artifact are addressed if the same is being shipped as part of the product delivery to the client	I		S	C				I	R				S	S		S
	Conduct periodic audits			C					A	R	S			C	S		S
Testing				S					S	S	R
Empowerment and Decision-Making		I				I	I		A	R
Staffing		I				I	I		A	R	I					S
Career Development					R					A	S	I					I	S
Performance Management					I	A					R
Mentoring					I	A	R	S					S
Internal Communication					I				I	A	R					I
Process Appraisals					I		A	R	R	S					S	I
Management Review					S	R	S				I		S
Preventive and Corrective action					I	A	S					R
Continual Improvement					I	A	S	S					R		I	S
Quality Management					I	A					S		R
Training & Competency Development					I					A	R					S	S
Work Environment Management					I		A	R

## OPD
Operational Process Definition				TOC

Project's OPD

Project operational process is defined in the below attachment.